## bfi
Sl No | Objective 1 | Key results |  | Initiatives | DFS | BFI | Timeline | Priority | Status | Progress
1 | Hire core IDFS team
1.1 |  | Complete interviews and Finalise Candidates |  | Interviews and finalization | Ramnath | Naga | 2023-10-31 | High | Ongoing | 50%
1.2 |  | Complete Onboarding |  | Contract signing with BVT | Ramnath | Naga | 2023-11-15 | Low | Ongoing | 20%
2 | Launch HCD Fellowship
2.1 |  | Onboarding the Partners Process |  | Set up onboarding process, Submittables, meeting and workshop | VSR - Knowledge and Research Lead | Naga | 2023-10-31 | High | Ongoing | 0%
2.2 |  | Receive the applications from Partners |  | Launch the submitables + Finalise partners | VSR - Knowledge and Research Lead | Naga | 2023-11-30 | High | Yet to Start | 0%
2.3 |  | Fellowship Design |  | Design Fellowship + Finalise the program + tools | HCD Lead | Naga | 2023-12-31 | High | Ongoing | 30%
2.4 |  | Launch Fellowship |  | Workshop + Launch | HCD Lead | Naga | 2024-02-05 | High | Yet to Start | 0%
2.5 |  | MOU with Districts is signed |  | Workshop + Drafting of MOU+ Signing of MOU | Ramnath & Girish | Naga | 2024-02-15 | High | Yet to Start | 0%
3 | Launch IHCR Fund
3.1 |  | Finalise the Deck + TOR |  | Workout the TOR Design the Deck | VSR - Knowledge and Research Lead | Naga | 2023-10-21 | High | Ongoing | 50%
3.2 |  | Strategic Partnerships are identified + meetings |  | Stakeholder mapping + Meetings | Ramnath | Naga |  | High | Ongoing | 10%
3.3 |  | Onboarding Partners |  | Ceate anlignmet + Processes +strategic Partners | Ramnath | Naga |  | High | Ongoing | 0%
3 | Regular Program Monitoring + Team Governance
3.1 |  | Regular Team Updated meeting |  | with BFI team and CEO | Ramnath | Naga |  | High | Ongoing | 50% | Every 2nd Thursday
3.2 |  | Regular Communication + Social Media Updates |  | DFS Team will send weekly relevant updates | Ramnath | Naga |  | High | Ongoing | 40% | Weekly
|  | Blockchain For Impact - India District Health Stack Fund | [6 empty] | Timeframe | Progress
|  | Vision | Blockchain for an equitable world | [5 empty] | Q4 2023 | 21%
Project Name
|  | Outcomes | Build a team to enable a ground up public problem ecosystem across India by 2028
Launch a national wide India Health and Climate Resilience Fund (IHCR- Fund)